## Project Planner
Project 3
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 56 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Period N = Day N since project details announced), Day 1 = May 3rd 2022
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
PLANNING PHASE | 1 | 3 | 1 | 3 | 100%
Read Project Specs + Come up with questions for Heller + Ask Heller | 1 | 1 | 1 | 1 | 100%
look at the flat file and see how to break it up into different tables + make plan PDF. Also look into things that need to be cleaned and clean them | 1 | 3 | 1 | 3 | 100%
Review Plan | 3 | 1 | 3 | 1 | 100%
IMPLEMENTATION PHASE | 4 | 4 | 4 | 4 | 100%
Set up the tables based on plan PDF + setup cleaning and FK-related procedures | 4 | 1 | 4 | 1 | 100%
Set up inline TVFs | 4 | 2 | 4 | 2 | 100%
Compile functions + setup procedures for them + setup other procedures | 6 | 1 | 6 | 1 | 100%
Make queries | 6 | 2 | 6 | 2 | 100%
PRESENTATION PHASE | 8 | 6 | 8 | 6 | 100%
Get slides into recordable state | 8 | 2 | 8 | 3 | 100%
Do recordings + complete slides | 9 | 4 | 10 | 3 | 100%
Compile work + make final database backup + make database script + sumbit | 13 | 1 | 13 | 1 | 100%