## Timothy
To-do list
To be completed by: |  | 2022-05-15 |  | Timothy Dakis
Deadline: |  |  |  | 2022-05-15
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Specs + Come up with questions for Heller + Ask Heller | 2022-05-03 | 2022-05-03 |  | 0
100% | look at the flat file and see how to break it up into different tables + make plan PDF. Also look into things that need to be cleaned and clean them | 2022-05-03 | 2022-05-05 |  | 2
100% | Review plan | 2022-05-05 | 2022-05-05 |  | 0
100% | Set up the tables based on plan PDF + make an example function + setup cleaning and FK-related procedures | 2022-05-06 | 2022-05-06 |  | 0
100% | Set up inline TVFs used to fill tables | 2022-05-06 | 2022-05-07 |  | 1
100% | Compile functions + setup the procedures for them, as well as setting up any other procedures needed | 2022-05-08 | 2022-05-08 |  | 0
100% | Set up queries | 2022-05-08 | 2022-05-09 |  | 1
100% | Get slides to point where recordings can be started | 2022-05-10 | 2022-05-12 |  | 2
100% | Fully complete slides + do recording | 2022-05-12 | 2022-05-14 |  | 2
100% | Compile all recordings + make final back up + make database creation script + submit work | 2022-05-15 | 2022-05-15 |  | 0

## Mikhaeil
To-do list
To be completed by: |  | 2022-05-14 |  | Mikhaiel Gomes
Deadline: |  |  |  | 2022-05-15
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into flat file and give suggestions to group leader | 2022-05-03 | 2022-05-05 |  | 2
100% | Review the plan | 2022-05-05 | 2022-05-05 |  | 0
100% | Make assigned functions | 2022-05-06 | 2022-05-07 |  | 1
100% | Make queries | 2022-05-08 | 2022-05-09 |  | 1
100% | Do recordings | 2022-05-12 | 2022-05-14 |  | 2

## Shivanie
To-do list
To be completed by: |  | 2022-05-14 |  | Shivanie Kemraj
Deadline: |  |  |  | 2022-05-15
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into flat file and give suggestions to group leader | 2022-05-03 | 2022-05-05 |  | 2
100% | Review the plan | 2022-05-05 | 2022-05-05 |  | 0
100% | Make assigned functions | 2022-05-06 | 2022-05-07 |  | 1
100% | Make queries | 2022-05-08 | 2022-05-09 |  | 1
100% | Do recordings | 2022-05-12 | 2022-05-14 |  | 2

## Konrad
To-do list
To be completed by: |  | 2022-05-14 |  | Konrad Rakowski
Deadline: |  |  |  | 2022-05-15
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into flat file and give suggestions to group leader | 2022-05-03 | 2022-05-05 |  | 2
100% | Review the plan | 2022-05-05 | 2022-05-05 |  | 0
100% | Make assigned functions | 2022-05-06 | 2022-05-07 |  | 1
100% | Make queries | 2022-05-08 | 2022-05-09 |  | 1
100% | Do recordings | 2022-05-12 | 2022-05-14 |  | 2

## Kevin
To-do list
To be completed by: |  | 2022-05-15 |  | Kevin Tang
Deadline: |  |  |  | 2022-05-15
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into flat file and give suggestions to group leader | 2022-05-03 | 2022-05-05 |  | 2
100% | Review the plan | 2022-05-05 | 2022-05-05 |  | 0
100% | Make assigned functions | 2022-05-06 | 2022-05-07 |  | 1
100% | Make queries | 2022-05-08 | 2022-05-09 |  | 1
100% | Do recordings | 2022-05-12 | 2022-05-14 |  | 2