## Timothy
To-do list
To be completed by: |  | 2022-03-12 |  | Timothy Dakis
Deadline: |  |  |  | 2022-03-13
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning + JDBC | 2022-02-27 | 2022-03-01 |  | 2
100% | 20 Queries | 2022-03-01 | 2022-03-04 |  | 3
100% | Start PowerPoint Slides + Creation of Template | 2022-03-05 | 2022-03-06 |  | 1
100% | Record individual + group queries on ppt | 2022-03-06 | 2022-03-11 |  | 5
100% | Record JDBC (explain + execute) | 2022-03-06 | 2022-03-11 |  | 5
100% | Merge all filled templates into main slides + add project management part and record it | 2022-03-08 | 2022-03-11 |  | 3
100% | Make the individual pdfs for each person's 9 queries using information from ppt templates | 2022-03-08 | 2022-03-12 |  | 4
100% | Compile all work + merge all pptx mp4s into final pptx mp4 | 2022-03-11 | 2022-03-12 |  | 1
100% | Submit Work | 2022-03-12 | 2022-03-13 |  | 1

## Mikhaeil
To-do list
To be completed by: |  |  |  | Mikhaiel Gomes
Deadline: |  |  |  | 2022-03-12
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | 20 Queries | 2022-03-01 | 2022-03-06 |  | 5
100% | Fill in powerpoint template | 2022-03-06 | 2022-03-08 |  | 2
100% | Record individual section of slides + execution of jdbc | 2022-03-09 | 2022-03-11 |  | 2

## Shivanie
To-do list
To be completed by: |  | 2022-03-11 |  | Shivanie Kemraj
Deadline: |  |  |  | 2022-03-13
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | 20 Queries | 2022-03-01 | 2022-03-06 |  | 5
100% | Fill in powerpoint template | 2022-03-06 | 2022-03-08 |  | 2
100% | Record individual section of slides + execution of jdbc | 2022-03-09 | 2022-03-11 |  | 2

## Konrad
To-do list
To be completed by: |  | 2022-03-11 |  | Konrad Rakowski
Deadline: |  |  |  | 2022-03-13
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | 20 Queries | 2022-03-01 | 2022-03-06 |  | 5
100% | Fill in powerpoint template | 2022-03-06 | 2022-03-08 |  | 2
100% | Record individual section of slides | 2022-03-09 | 2022-03-11 |  | 2

## Kevin
To-do list
To be completed by: |  | 2022-03-11 |  | Kevin Tang
Deadline: |  |  |  | 2022-03-13
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | 20 Queries | 2022-03-01 | 2022-03-06 |  | 5
100% | Fill in powerpoint template | 2022-03-06 | 2022-03-08 |  | 2
100% | Record individual section of slides + execution of jdbc | 2022-03-09 | 2022-03-11 |  | 2