## Project Planner
Project 2.5
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 56 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Period N = Day N since project details announced), Day 1 = April 14th 2022
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
PLANNING PHASE | 1 | 4 | 1 | 4 | 100%
Read Project Specs + Come up with questions for Heller + Ask Heller | 1 | 1 | 1 | 1 | 100%
Look through Data schema tables and decide what tables to split (and how), what constraints to be made, what columns to be added/removed, what UDT should be made. After that post the ideas for review. | 1 | 4 | 1 | 4 | 100%
IMPLEMENTATION PHASE | 4 | 8 | 4 | 8 | 100%
Properly setup UDTs and other foundations | 4 | 1 | 4 | 1 | 100%
Normalize assiged Data schema tables | 5 | 2 | 5 | 2 | 100%
Compile work + correct any issues | 6 | 2 | 6 | 2 | 100%
Convert non-Data schema tables into views / functions where applicable | 8 | 3 | 8 | 3 | 100%
Compile work + correct any issues | 11 | 1 | 11 | 1 | 100%
Double check database for any final data cleansing issues and other issues | 11 | 1 | 11 | 1 | 100%
PRESENTATION PHASE | 11 | 7 | 11 | 7 | 100%
Get slides into recordable state | 11 | 4 | 11 | 4 | 100%
Do recordings + complete slides | 14 | 4 | 14 | 4 | 100%
Compile work + make final database backup + make database script + sumbit | 18 | 1 | 18 | 1 | 100%