## Timothy
To-do list
To be completed by: |  | 2022-05-01 |  | Timothy Dakis
Deadline: |  |  |  | 2022-05-01
Project 2.5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Specs + Come up with questions for Heller + Ask Heller | 2022-04-14 | 2022-04-14 |  | 0
100% | Look through Data schema tables and decide what tables to split (and how), what constraints to be made, what columns to be added/removed, what UDT should be made. After that post the ideas for review. | 2022-04-14 | 2022-04-17 |  | 3
100% | Review plan | 2022-04-17 | 2022-04-18 |  | 1
100% | Look into and properly set up the UDTs | 2022-04-17 | 2022-04-18 |  | 1
100% | Set up foundation for group to be able to start doing work, and do an example normalization for group | 2022-04-18 | 2022-04-18 |  | 0
100% | Normalize 2 assigned tables | 2022-04-18 | 2022-04-19 |  | 1
100% | Compile all converted Data schema tables + correct any issues + replace all "New" prefixed tables so that instead it uses initial table name | 2022-04-19 | 2022-04-20 |  | 1
100% | Update column data types for 6 assigned non-Data schema tables + add 3 columns used for tracking user authorization + establish FK to UserAuthorization table | 2022-04-21 | 2022-04-23 |  | 2
100% | Do final check for things related to data cleansing + compile all made views / functions | 2022-04-24 | 2022-04-24 |  | 0
100% | Get slides to point where recordings can be started | 2022-04-24 | 2022-04-27 |  | 3
100% | Fully complete slides + do recording | 2022-04-27 | 2022-04-30 |  | 3
100% | Compile all recordings + make final back up + make database creation script + submit work | 2022-05-01 | 2022-05-01 |  | 0

## Mikhaeil
To-do list
To be completed by: |  | 30/04/2022 |  | Mikhaiel Gomes
Deadline: |  |  |  | 2022-05-01
Project 2.5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into database and give suggestions to group leader | 2022-04-14 | 2022-04-17 |  | 3
100% | Review the plan | 2022-04-17 | 2022-04-18 |  | 1
100% | Normalize 1 assigned table | 2022-04-18 | 2022-04-19 |  | 1
100% | Convert 4 assigned non-Data schema tables into a view / functions | 2022-04-21 | 2022-04-23 |  | 2
100% | Double check database + versions of slides while slides are being made | 2022-04-24 | 2022-04-27 |  | 3
100% | Do recordings | 2022-04-27 | 2022-04-30 |  | 3

## Shivanie
To-do list
To be completed by: |  | 30/04/2022 |  | Shivanie Kemraj
Deadline: |  |  |  | 2022-05-01
Project 2.5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into database and give suggestions to group leader | 2022-04-14 | 2022-04-17 |  | 3
100% | Review the plan | 2022-04-17 | 2022-04-18 |  | 1
100% | Normalize 1 assigned table | 2022-04-18 | 2022-04-19 |  | 1
100% | Convert 2 assigned non-Data schema tables into a view / functions | 2022-04-21 | 2022-04-23 |  | 2
100% | Double check database + versions of slides while slides are being made | 2022-04-24 | 2022-04-27 |  | 3
100% | Do recordings | 2022-04-27 | 2022-04-30 |  | 3

## Konrad
To-do list
To be completed by: |  | 30/04/2022 |  | Konrad Rakowski
Deadline: |  |  |  | 2022-05-01
Project 2.5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into database and give suggestions to group leader | 2022-04-14 | 2022-04-17 |  | 3
100% | Review the plan | 2022-04-17 | 2022-04-18 |  | 1
100% | Normalize 1 assigned table | 2022-04-18 | 2022-04-19 |  | 1
100% | Convert 2 assigned non-Data schema tables into a view / functions | 2022-04-21 | 2022-04-23 |  | 2
100% | Double check database + versions of slides while slides are being made | 2022-04-24 | 2022-04-27 |  | 3
100% | Do recordings | 2022-04-27 | 2022-04-30 |  | 3

## Kevin
To-do list
To be completed by: |  | 30/04/2022 |  | Kevin Tang
Deadline: |  |  |  | 2022-05-01
Project 2.5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Look into database and give suggestions to group leader | 2022-04-14 | 2022-04-17 |  | 3
100% | Review the plan | 2022-04-17 | 2022-04-18 |  | 1
100% | Normalize 2 assigned table | 2022-04-18 | 2022-04-19 |  | 1
100% | Convert 2 assigned non-Data schema tables into a view / functions | 2022-04-21 | 2022-04-23 |  | 2
100% | Double check database + versions of slides while slides are being made | 2022-04-24 | 2022-04-27 |  | 3
100% | Do recordings | 2022-04-27 | 2022-04-30 |  | 3