## Project Planner
Project 2
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 56 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Period N = Day N since project details announced), Day 1 = March 29th
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Read project specs + Come up with questions | 1 | 2 | 1 | 2 | 100%
Attend office hours with Heller | 3 | 1 | 3 | 1 | 100%
Make project plan | 3 | 1 | 3 | 1 | 100%
Restore database + add the 3 columns | 3 | 1 | 3 | 1 | 100%
Make example procedure | 3 | 1 | 3 | 1 | 100%
Set up components needed for assigned procedure | 3 | 1 | 3 | 1 | 100%
Make assigned procedures | 3 | 3 | 3 | 3 | 100%
Clean up procedures and add to database + Make most slides | 5 | 2 | 5 | 2 | 100%
Make screenshots for slides | 6 | 3 | 6 | 3 | 100%
Finish slides | 8 | 1 | 8 | 1 | 100%
Last minute fixes + minor JDBC update + queries for JDBC video made | 8 | 2 | 8 | 2 | 100%
Recordings for Powerpoint and JDBC videos made | 8 | 5 | 9 | 4 | 100%
Compile all work + made Redgate pdf + final backup + submit work | 13 | 1 | 13 | 1 | 100%