## Timothy
To-do list
To be completed by: |  | 2022-10-04 |  | Timothy Dakis
Deadline: |  |  |  | 2022-04-13
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Specs + Come up with questions for Heller | 2022-03-29 | 2022-03-30 |  | 1
100% | Ask Heller questions + Come up with Project Plan | 2022-03-31 | 2022-03-31 |  | 0
100% | Restore Database + add columns to tables | 2022-03-31 | 2022-03-31 |  | 0
100% | Make procedure as an example + supply code necessary to set up components needed by group to make their assigned procedures | 2022-03-31 | 2022-03-31 |  | 0
100% | Make 11 assigned procedures | 2022-03-31 | 2022-04-02 |  | 2 | Unbalanced number of procedures to accommodate fact group members were very busy with other projects and exams
100% | Clean up procedures + set up the master version of database to have all procedures properly loaded + Send a backup of said master to group to restore + Make most of the slides | 2022-04-02 | 2022-04-03 |  | 1
100% | Get slides finished | 2022-04-05 | 2022-04-05 |  | 0
100% | Last minute fixes + minor JDBC update + create queries for each group member to execute for JDBC video + Send out more recent version of master database | 2022-04-05 | 2022-04-06 |  | 1
100% | Record clips for powerpoint recording and JDBC recording | 2022-04-06 | 2022-04-09 |  | 3
100% | Compile all work + create final backup + generated Redgate PDF + Submit Work | 2022-04-10 | 2022-04-10 |  | 0

## Mikhaeil
To-do list
To be completed by: |  | 2022-09-04 |  | Mikhaiel Gomes
Deadline: |  |  |  | 2022-04-13
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Specs + Come up with questions for Heller | 2022-03-29 | 2022-03-30 |  | 1
100% | Restore Database + add columns to tables | 2022-03-31 | 2022-03-31 |  | 0
100% | Make 2 assigned procedures | 2022-03-31 | 2022-04-02 |  | 2
100% | Restore more recent database + submit necessary screenshots for slides | 2022-04-03 | 2022-04-05 |  | 2
100% | Restore more recent version of master database + Record clips for powerpoint recording and JDBC recording | 2022-04-06 | 2022-04-09 |  | 3

## Shivanie
To-do list
To be completed by: |  | 2022-03-11 |  | Shivanie Kemraj
Deadline: |  |  |  | 2022-04-13
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Specs + Come up with questions for Heller | 2022-03-29 | 2022-03-30 |  | 1
100% | Restore Database + add columns to tables | 2022-03-31 | 2022-03-31 |  | 0
100% | Make 2 assigned procedures | 2022-03-31 | 2022-04-02 |  | 2
100% | Restore more recent database + submit necessary screenshots for slides | 2022-04-03 | 2022-04-05 |  | 2
100% | Restore more recent version of master database + Record clips for powerpoint recording and JDBC recording | 2022-04-06 | 2022-04-09 |  | 3

## Konrad
To-do list
To be completed by: |  | 2022-09-04 |  | Konrad Rakowski
Deadline: |  |  |  | 2022-04-13
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Specs + Come up with questions for Heller | 2022-03-29 | 2022-03-30 |  | 1
100% | Restore Database + add columns to tables | 2022-03-31 | 2022-03-31 |  | 0
100% | Make 1 assigned procedure | 2022-03-31 | 2022-04-02 |  | 2
100% | Restore more recent database + submit necessary screenshots for slides | 2022-04-03 | 2022-04-05 |  | 2
100% | Restore more recent version of master database + Record clips for powerpoint recording and JDBC recording | 2022-04-06 | 2022-04-09 |  | 3

## Kevin
To-do list
To be completed by: |  | 2022-09-04 |  | Kevin Tang
Deadline: |  |  |  | 2022-04-13
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Specs + Come up with questions for Heller | 2022-03-29 | 2022-03-30 |  | 1
100% | Restore Database + add columns to tables | 2022-03-31 | 2022-03-31 |  | 0
100% | Make 1 assigned procedure | 2022-03-31 | 2022-04-02 |  | 2
100% | Restore more recent database + submit necessary screenshots for slides | 2022-04-03 | 2022-04-05 |  | 2
100% | Restore more recent version of master database + Record clips for powerpoint recording and JDBC recording | 2022-04-06 | 2022-04-09 |  | 3